## Gantt Plan
Task | Owner | Start | Duration (days) | End | % Complete | Progress | W1 | W2 | W3 | W4 | W5 | W6
Project kick-off & brief | You | 2026-01-05 | 2 |  | 100%
Research & references | You | 2026-01-07 | 3 |  | 100%
First draft / wireframes | You | 2026-01-10 | 5 |  | 80%
Client review — round 1 | Client | 2026-01-15 | 3 |  | 60%
Revisions | You | 2026-01-18 | 4 |  | 40%
Final polish & QA | You | 2026-01-22 | 3 |  | 10%
Delivery & handover | You | 2026-01-25 | 2 |  | 0%
Follow-up & support window | You | 2026-01-27 | 5 |  | 0%
How to read this sheet: teal blocks in the week columns (W1–W6) show when each task runs; darker teal = the finished share. End dates and the Progress bar calculate themselves.
Example project below the header in the full pack: replace the sample tasks with your own.

## Milestones
Milestone | Owner | Due date | Status
Brief signed & deposit received | Client | 2026-01-05 | Done
First draft approved | Client | 2026-01-16 | In progress
Final delivery | You | 2026-01-27 | Not started
Project closed & invoice settled | Client | 2026-01-30 | Not started

## Budget
Category | Item | Planned | Actual | Variance (Planned − Actual)
Tools | Software subscription (project month) | 40 | 40
Stock & assets | Stock images / fonts licence | 60 | 45
Subcontracting | Proofreader for final pass | 150 | 150
Marketing | Portfolio update & case study | 30 | 0
Contingency | Buffer for surprises (keep untouched if possible) | 100 | 0
TOTAL